## Test Script
Test Script:
Tested by: | Luis Rodriguez
Date: | 2020-04-21
Browser: | Internet Explorer
Web Page: | Test No: | Test: | Check (Yes/No): | Comments (notes/improvements):
Create Account | 1 | Without being logged in, try to access any of the pages in the red menu. You should be redirected back to the log in page each time | Yes
| 2 | From the log in page, click the 'Sign Up' button. You should be redirected to the Sign Up page | Yes
| 3 | Try to enter more than 4 letters to the Username text box. You should not be able to | Yes | Hover above say 3 letter code
| 4 | For your email, use your personal email address. Fill out the rest of the fields correctly. Click the Register button. It should throw an error, prompting a Clarksons email address to be used | Yes | email address error was not obvious on top of the form and small font
| 5 | Clear the form and fill out all relevant fields. This time make sure the passwords do not match. Click Register. An error should be thrown | Yes
| 6 | Try to register without ticking the terms and conditions box. An error should be prompted | Yes
| 7 | Fill out all fields correctly. Press 'Register'. You should be redirected to the home page | Yes
| 8 | Once logged in, you should be able to view your username in the top right hand corner | Yes
Login: | 9 | Log out. Your username should no longer be visible | Yes
| 10 | Try to log in using false credentials. An error should appear | Yes
| 11 | Enter your username, but leave the password blank. Click 'Log In'. You should be prompted to enter a password | Yes
| 12 | Try to log in using your relevant credentials. You should be redirected to the Home page | Yes
Home: | 13 | You should be able to see multiple charts displaying a range of football statistics | Yes
| 14 | Hover over the 'Home' button. Click each of the drop-down options and check each page has data. (Note: Power Bi section will not have any data displayed) | Yes
| 15 | On the home page, select a QR code from the drop-down menu. A QR code should then be displayed | Yes
| 16 | Using your mobile phone, scan the QR code. This can be done via any QR scanning application. It should redirect you to the Power Bi application (if you do not have this installed, please install it) | Yes
| 17 | You should then be able to see the Power Bi chart. | NO | Uses luis@clarkson email. Error saying cannot access this account
Profile: | 18 | Click the 'My Profile' button in the red tab. You should be redirected to your profile page | Yes
| 19 | Where it says 'Welcome back…', check that your name is displayed correctly | Yes
| 20 | So far the information in your profile should be blank. Check that this is the case (i.e. there is no nickname, position etc.) | Yes
| 21 | To change this, click the 'Edit' button. You should be redirected to a page where you can edit the information | Yes
| 22 | You should be able to edit all information other than the number of appearances, number of goals and your performance index. Check this is the case | Yes
| 23 | Change some of the information on the page. Click Submit. You should be redirected back to your profile | NO | No info on the page to edit
| 24 | Check that the information has been updated with the new data | Yes
| 25 | Try to edit your profile photo by clicking the 'Edit' button once again. You should be able to select any PNG or JPG file. | Yes
| 26 | Check this gets updated when you click 'Submit' | NO | error in field "POSITION"
| 27 | Click the 'Gallery' button in the red tab. You should be redirected to everyone's profile page | Yes
| 28 | So far, your profile should not appear here yet. Check this is the case | Yes
| 29 | Go back to your profile, and click 'Add Profile to Gallery'. | Yes
Gallery: | 30 | Go back to the gallery by pressing 'Gallery'. Your profile should now be displayed here | Yes
| 31 | Check that the information is correct and you cannot make any changes to it | Yes
| 32 | Check that you cannot see anyone else's performance index | Yes
| 33 | Change the size of your window to see if the gallery responds accordingly | Yes
Match Day: | 34 | Click on the 'Match Day' button in the red tab. You should be redirected to the match day page | Yes
| 35 | Check that the next fixture's date is in the future | Yes
| 36 | Check to see if anyone is playing in the upcoming fixture | Yes
| 37 | Check that there is data being displayed for the previous game | Yes
| 38 | Check that the date is in the past and that there is a visible final score | Yes
| 39 | Check that the number of goal scorers matches the final score in both teams | Yes
| 40 | Check that there is a Graph of the Week with data | Yes
To be able to test the next stage, you need to request admin permission. To do this, click on your username in the top right hand corner and wait for next instructions.
Admin: | 41 | Hover over the Admin button in the red tab. There should be two drop-down options | Yes
New Match: | 42 | Click 'New Match'. You should be redirected to the new match form | Yes
| 43 | Check you can input a date for the upcoming match. Enter a sensible date (i.e. within the next week for example). Make a note of this date | Yes
| 44 | Check that there is a list of players and each one has a performance index (should be around 30-40 names) | Yes
| 45 | Change the ordering of the players using the drop-down menu. Check that the grid updates accordingly | Yes
| 46 | Click the 'Auto Generate Teams' button. Check that five names from each team has been randomly selected | Yes
| 47 | Unclick the Auto Generate button. Now select the teams yourself by clicking different usernames. Check that a player cannot play for both the Yellow and Orange team | Yes
| 48 | At the bottom of the page is a preview section. Having clicked on a player, check that their name gets populated here correctly | Yes
| 49 | Click the 'Submit' button. You should be redirected to the Match Day page | Yes
| 50 | Check that this has been updated with the new match (i.e. next fixture is the new match and teams have updated) | Yes
Results: | 51 | Hover over the Admin button and click on 'Results' | Yes
| 52 | Check the date is the same as the date you entered in step 43 | Yes
| 53 | In any of the text boxes, try to enter some characters that are NOT numbers. You should only be able to enter numbers | Yes
| 54 | Check that each text box allows you to click up and down to select the number of goals scored | Yes
| 55 | By clicking, check that you cannot score less than 0 goals, or more than 15 | Yes
| 56 | Check that the final score changes dynamically based on the number of goals scored per player | Yes
| 57 | Check you can select more than one player who has dropped out | Yes
| 58 | Press 'Submit'. You should be redirected back to the match day page | Yes
| 59 | Check that the 'Previous Game' results have been updated with the latest data | NO
Reset Password: | 60 | Press the Logout button. You should be redirected to the Login page | Yes
| 61 | From here, click the 'Forgot Password' button. You should be redirected to the Forgot Password page | Yes
| 62 | Enter your username and email address you wish to send a new password to. Click 'Send Email' | Yes
| 63 | You should receive an email (may be in your spam/junk folder) with the new password | Yes
| 64 | Try to log back in using this new password. You should be redirected to the home page and logged in successfully | Yes | Cant test as invalid email address
Data Visualisation | 65 | Finally, log out once more and log in with an existing 'test' account. Username: LSC P'word: asd | Yes
| 66 | Go to 'My Profile'. Check that there is a profile photo and at the bottom there are graphs with relevant data | Yes
| 67 | Hover over the button to add the profile to the gallery. This should be disabled. | Yes
| 68 | Check that 'LSC' (Liam Scott) profile is in the gallery | Yes
| 69 | Check that the 'Admin' button is visible in the menu bar | Yes
| 70 | On the home page, check that graphs have data being displayed | Yes